## Estimated
Project: PG&E Energy Reducer
Burndown Table
Timeline
| Estimated Effort | Actual Effort | Week
Product Backlog Inventory (PBI) |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Plan development of the app | 4 | 0
Write pre-interview notes | 1 | 1 | bar: Week 2
Hold first interview | 0.5 | 0.5 | Week 2: 0.5
Write pre-interview notes - 2 | 1 | 1 | bar: Week 3
Hold second meeting | 0.5 | 0
Write second app description | 1.5 | 0
Implement team website | 4 | 0
Work on interaction design | 2 | 0
Create cognitive walkthrough | 2 | 0
Give feedback on cognitive walkthrough | 1 | 0
Forms and File Upload | 3 | 0
Design Review | 2 | 0
Design Changes after Cog Walk | 3 | 0
Initial Github Commit | 1 | 0
Domain Commit | 0.5 | 0
Usability Test Scheduling | 0.5 | 0
UX Consultant Presentation | 3 | 0
First Deployment | 1 | 0
Final Design Presentation | 3 | 0
Final Design Feedback | 2 | 0
Design Changes | 3 | 0
Usability Testing | 3 | 0
Final Review With Client | 3 | 0
Remaining Effort |  | 2.5 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target: |  | 0
Burndown Graph